## Redirect map
Redirect mapper
Old URL → New URL. Flag chains and missing backlinks.
alstonantony.com/resources/
Old URL | New URL | HTTP status | Chain (>1 hop?) | Has backlinks? | Notes
/old-blog/seo-guide/ | /seo-guide/ | 301 | No | Yes (12 RDs) | Top page, verify first
/services/seo-audit/ | /resources/seo-marketing-audit-template/ | 301 | No | Yes (3 RDs) | Service page → resource
/blog/keyword-research-tips/ | /resources/keyword-research-template/ | 301 | No | Yes (5 RDs)
/about-us/ | /about/ | 301 | No | No
/category/wordpress/ |  | 404 | n/a | No | No equivalent. Let it 404.

## Pre-launch checks
Pre-launch checks
Complete these before deploying the new site.
alstonantony.com/resources/
Check | Done? | Notes
PRE-LAUNCH: REDIRECT MAPPING
Crawl the old site completely, every URL, not just the ones you remember
Export backlinks from Ahrefs or Search Console and match to old URLs
Map every old URL to the closest equivalent new URL, one to one
Prioritise redirects for pages with backlinks, those are irreplaceable
Use 301 (permanent) redirects, not 302 (temporary)
One hop per redirect, no chains through intermediate URLs
Never redirect to the homepage unless the old page genuinely was the homepage
Test a sample of 20 redirects on staging before launch
PRE-LAUNCH: CONTENT AND ANALYTICS
Run a content audit, pages worth nothing do not need redirecting
Confirm the analytics tag fires on the staging site, exactly once
Set up Search Console for the new domain or property before launch
Verify Bing Webmaster Tools for the new property
Back up the old site completely, files and database
Note current indexed page count and organic traffic as the baseline
Remove any noindex or robots.txt blocks left from the staging environment
Check that the new XML sitemap lists only canonical, indexable URLs
PRE-LAUNCH: TECHNICAL
Crawl the new site on staging and fix broken internal links
Confirm one hostname only, www or apex, with a single-hop redirect
HTTPS is enforced, no mixed content warnings
Canonical tags on the new site point to the new URLs, not the old ones
Trailing slash policy is consistent across the new site
Hreflang tags updated if the site is multilingual
Structured data updated to reflect new URLs

## Post-launch monitor
Post-launch monitor
Track these weekly for 8 weeks after migration.
alstonantony.com/resources/
Week | Indexed pages | Organic traffic | New 404s | Notes
Baseline
Week 1
Week 2
Week 3
Week 4
Week 5
Week 6
Week 7
Week 8